## BCSED
Last Updated by: Mike Dioquino Revised Date: 12/09/2011 | [11 empty] | Business Work Flow | 1 | Open
BCSED - Recommendation Log | [11 empty] | Support |  | Closed
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Notes | Cost | Data Conversion | 3
1 | BCSED | 2010-11-01 | Support | Technical support staff hours should be adjusted to cover all instructional lab hours | 1 | Closed | ITS | ASAP | N/A | Computer Services Tech is now on duty each night until 10:00 pm to address faculty instructional needs | N/A | Functionality | 4
2 | BCSED | 2010-11-01 | Support | The Palmdale Center computer lab should have a telephone located in the computer lab | 3 | Closed | ITS | ASAP | N/A | As of 11-08-2011 telephones have been installed in Palmdale campus classroom/labs. Purchase of phone issue resolved. | N/A | Technical Work Flow
3 | BCSED | 2010-11-01 | Technical Work Flow | Processes should be developed and formalized for requesting, installing, testing, and verifying the operation of instructional software | 3 | Open | ITS | ASAP | Review existing process and carry forward to IT Committee for appropriate resolution. | 12/06/2011: Division will be presented with a baseline config by ITS. Division will approve baseline config. Teachers with other software needs will fill out a survey on what they require. Survey must be returned to ITS in a timely fashion. Teacher verification of installation is also available so they may pre enter identity fields. That also must be done in a timely fashion in conjunction with the image creation. Report survey to assigned ITS personnel. | N/A | Project | 4
4 | BCSED | 2010-11-01 | Support | Technical support technicians who would be supporting the instructional labs should become part of the BCSED Division and report to the division dean, while maintaining an organizational matrix connection to the ITS Department | 3 | Closed | ITS | ASAP | N/A | Not relevant at this time. No justification for this because usually the Lab technician is assigned to each division. Lab Tech support issues should be included in Program Review and carried forward to SPBC process. | N/A |  | 5
5 | BCSED | 2010-11-01 | Functionality | All computers should be equipped with DVD drives and multiple USB ports accessible to students and instructors | 1 | Closed | ITS | ASAP | N/A | Non Issue. BCSED group decided that this should be USB drive instead of DVD. New computers help resolve issue with thin clients USB problems. | N/A
6 | BCSED | 2010-11-01 | Functionality | Select faculty should be granted access to the Deep Freeze configuration software as required | 3 | Closed | ITS | ASAP | N/A | None issue now because deep freeze option is now functioning like it should be. New Perkins Project computers will fix issue. | N/A
7 | BCSED | 2010-11-01 | Functionality | Faculty should be granted administrative rights to lab workstations to allow operation of Control Panel features, including the installation and un-installation of software | 2 | Closed | ITS | ASAP | Any issues concerning any limited Administrative Rights will be carried forward to IT Committee for analysis and approval. This option is taken up by the DETC Committee. | 12/06/2011: Related to CA103 classroom example. Standard configuration is automatically logs in as administrator (with administrative rights) for BE. | N/A
8 | BCSED | 2010-11-01 | Functionality | Computers in the instructional labs should be configured with two physical hard drives, one of which stores the Deep Freeze configuration for general instruction operations, and the other for managing Deep Freeze virtual images and storing VMWARE client operating systems | 1 | Closed | ITS | ASAP | N/A | This currently works; however if machine goes down then need thumb drive. ITS can work with instructors in the program requiring a configuration that is different from the configuration used in "general instruction" courses. | N/A
9 | BCSED | 2010-11-01 | Functionality | The file server should contain a common drive that would allow faculty and students to store, retrieve, and exchange data files | 1 | Closed | ITS | ASAP | Work with instructor on case-by-case scenario to resolve any issues. This should resolve itself with new Perkins Grant computers and implementation for Spring 2011 | Already in place for many courses; however this will be addressed in the Open Digital Campus Program integrating role based student authentication in active directory. | N/A
10 | BCSED | 2010-11-01 | Functionality | Instructional computer labs should be configured as fat clients with a network connection to a file server and to the Internet. Additionally, workstations should be configured to operate in a standalone mode of operation in the event network communication is lost. Workstation boot-up should not be dependent upon a connection to a server | 1 | Closed | ITS | ASAP | N/A | With the implementation of the Perkin Project Computers this will be addressed. The new computers will be stand-alone with no thin client or "blade PC" configurations | N/A
11 | BCSED | 2011-12-06 | Project | Perkins Project Implementation | 1 | Open | ITS | 2012-02-05 | Procurement Process
12 | DETC | 2011-12-06 | Functionality | Ability to connect personal laptops to internet and/or projector | 3 | Open | ITS | 2012-08-20
13 | BCSED | 2011-12-06 | Project | Implementation of virtual oracle server into production. |  | Open | ITS | TBD | Need to test config for workstations and also price out equipment needed.
14 | BCSED | 2011-12-06 | Support | Quickbooks need to be available on all lab workstations. |  | Open | ITS | TBD | 12/08/11 Sent an email to Jen@CDW detailing the requirements of the division. Waiting for a response from her.
15 | BCSED | 2011-12-06 | Business Work Flow | Upload updated versions of Recommendation Log onto myAVC. |  | Closed | ITS | ASAP |  | Updated versions of Rec Log will be uploaded by ITS personnel when changes are made to myAVC portal. Document will be placed in ITS Documents section. | N/A
16 | BCSED | 2011-12-06 | Functionality | Instructor workstations take too long. |  | Open | ITS | TBD | Review baseline image with division and make recommendations for possible cost effective solutions.
17 | BCSED | 2011-12-06 | Functionality | Workstations disrupted by Windows Update. |  | Open | ITS | TBD | Review GPO to ensure updating does not force restart.
18 | BCSED | 2011-12-06 | Business Work Flow | Update on Palmdale IT for VP and Deans. |  | Open | ITS | TBD
19 | BCSED | 2011-12-06 | Functionality | Powersave causing computers to shut down. |  | Open | ITS | TBD | Need to schedule meeting with Business Svcs and Chevron to find out requirements and support.
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## Health & Science
Last Updated by: Mike Dioquino Revised Date: 12/09/2011 | [11 empty] | Business Work Flow | 1 | Open
Health Sciences - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Notes | Cost | Data Conversion | 3
1 | Health Science | 2011-12-05 | Functionality | Wireless access in the new Health and Sciences building. |  | Open | ITS | TBD | Planning stage. |  |  | Functionality | 4
2 | Health Science | 2011-12-05 | Support | Tech support for division during night hours and Fridays. |  | Closed | ITS | ASAP |  | Computer Services Tech is now on duty each night until 10:00 pm to address faculty instructional needs |  | Technical Work Flow
3 | Health Science | 2011-12-05 | Support | Replacement workstations for staff not moving to new Health and Science building. |  | Open | ITS | TBD |  |  |  | Project | 4
4 | Health Science | 2011-12-05 | Support | Computers that do not have Win 7 and/or Office 2010 need to be upgraded in order to accommodate software. |  | Open | ITS | TBD |  |  |  |  | 5
5 | Health Science | 2011-12-05 | Support | Support for human patient simulators. |  | Open | ITS | TBD |  | 12/5/11 Laptops are connected to simulators. Need sound, mics, dual screens to be confirmed as functional and reliable.
6 | Health Science | 2011-12-05 | Support | IMC/ITS support routed back and forth. |  | Open | ITS | TBD
7 | Health Science | 2011-12-05 | Support | Podium wiring a mess, leading to wiring getting disconnected. |  | Open | ITS | TBD
8 | Health Science | 2011-12-05 | Functionality | Podcast support |  | Open | ITS | TBD
9 | Health Science | 2011-12-05 | Support | Issue at Palmdale site where computer was locked and not accessible. |  | Open | ITS | TBD
10 | Health Science | 2011-12-05 | Support | C&S need educational software installed. |  | Open | ITS | TBD
11 | Health Science | 2011-12-05 | Functionality | RealTime, QuickTime, Flash Player need to be installed on workstations. |  | Open | ITS | TBD
12 | Health Science | 2011-12-05 | Project | CDC/CNS classrooms 102, 106, 108, 112 need network drops installed. |  | Open | ITS | TBD
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## OSD
Last Updated by: Mike Dioquino Revised Date: 12/09/2011 | [11 empty] | Business Work Flow | 1 | Open
OSD - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Notes | Cost | Data Conversion | 3
1 | OSD | 2011-12-09 | Support | PC or thin client deployed at OSD counter for student use. |  | Open | ITS | TBD |  |  |  | Functionality | 4
2 | OSD | 2011-12-09 | Functionality | Install Office 2010 in T100 O, N R, S, T, and J. OSD proctored exams require Office 2010. |  | Open | ITS | TBD |  |  |  | Technical Work Flow
3 | OSD | 2011-12-09 | Project | Install accessible software on all campus workstations so all workstations are accessible by persons with disabilities. |  | Open | ITS | TBD |  |  |  | Project | 4
4 | OSD | 2011-12-09 | Project | Caption streaming audio of class lectures. |  | Open | ITS | TBD |  |  |  |  | 5
5 | OSD | 2011-12-09 | Project | Any newly acquired campus wide technology needs to be accessible by persons with disabilities. |  | Open | ITS | TBD
6 | OSD | 2011-12-09 | Project | Plan for the acquisition of access technology software when new buildings, labs, and classrooms come online. |  | Open | ITS | TBD
7 | OSD | 2011-12-09 | Project | Keep current with all access software maintenance agreements. |  | Open | ITS | TBD
8 | OSD | 2011-12-09 | Support | Establish a once a semester meeting with OSD, Alternative Media Specialist, and ITS Director in order to communicate any issues. |  | Closed | ITS | TBD |  | Part of the accreditation recommendation, ITS Director will meet with OSD every quarter to review past issues and document any new issues.
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## ASO
Last Updated by: Calvin Madlock Revised Date: 12/19/2011 | [11 empty] | Business Work Flow | 1 | Open
ASO - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Notes | Cost | Data Conversion | 3
1 | ASO | 2011-10-27 | Functionality | Banner is arbitrarily terminating sessions |  | Open | ITS | TBD | Report to IT Programming Manager for Analysis & Resolution |  |  | Functionality | 4
2 | ASO | 2011-10-27 | Support | Respiratory Therapy Students - Cannot Access C&S Medical Education Software in Learning Center |  | Closed | ITS (Bryan Spidell) | ASAP | N/A | Bryan installed software on 2, machines (SBI 1 & 2). 11/4/2011: Calvin found other machines with software loaded (CAI 1 - 26). This real issue is due to not having an instructor available in nursing labs forcing students to use Learning center to complete assignments - |  | Functionality | 4
3 | ASO | 2011-10-27 | Functionality | Wireless Connectively |  | Open | ITS | TBD | ITS Committee | Student recommendation is to look into NetGear as wireless solution |  | Functionality | 4
4 | ASO | 2011-10-27 | Functionality | Simplify voting on campus software |  | Open | ITS | TBD | IT Analysis |  |  | Functionality | 4
4 | ASO | 2011-10-27 | Support | Email issues: not receiving, problems with updates, and linking |  | Open | ITS | TBD | ITS Analysis |  |  | Functionality | 4
4 | ASO | 2011-10-27 | Support | Concern with myAVC security |  | Open | ITS | TBD | ITS Analysis |  |  | Functionality | 4
4 | ASO | [10 empty] | Functionality | 4
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## Learning Center
Last Updated by: Calvin Madlock Revised Date: 12/19/2011 | [11 empty] | Business Work Flow | 1 | Open
Learning Center - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Root Cause/Notes | Cost | Data Conversion | 3
1 | LC | 2011-11-04 | Support | Issues with Internet in room LC104 |  | Open | ITS - Bryan Spidell | TBD | ITS Analysis |  |  | Functionality | 4
2 | LC | 2011-11-04 | Functionality | Various computers disconnecting from network |  | Open | ITS - B. Spidell | ASAP | ITS Analysis | Learning Center not services during Summer 2011 |  | Functionality | 4
3 | LC | 2011-11-04 | Support | Issues with assisted technolgy in Palmdale |  | Open | ITS - B. Arceneaux | TBD | ITS Analysis |  |  | Functionality | 4
4 | LC | 2011-11-04 | Support | Issues with lead time with upgrading of software |  | Open | ITS - B. Spidell | TBD | IT Analysis |  |  | Functionality | 4
5 | LC | 2011-11-04 | Support | Identify where C&S Medical Education Software is loaded |  | Open | ITS - B. Spidell | TBD | ITS Analysis |  |  | Functionality | 4
6 | LC | 2011-11-04 | Support | Issues with computer wiring in LC |  | Open | ITS - W. Burnes | TBD | ITS Analysis |  |  | Functionality | 4
7 | LC | 2011-11-04 | Support | Error: the system cannot log in because the domain students is not availiable |  | Open | ITS | TBD | ITS Analysis |  |  | Functionality | 4
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## Language Arts
Last Updated by: Calvin Madlock Revised Date: 12/19/2011 | [11 empty] | Business Work Flow | 1 | Open
Language Arts - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Notes | Cost | Data Conversion | 3
1 | ASO | 2011-10-27 | Functionality | Banner is arbitrarily terminating sessions |  | Open | ITS | TBD | Report to IT Programming Manager for Analysis & Resolution |  |  | Functionality | 4
3 | ASO | 2011-10-27 | Functionality | Wireless Connectively |  | Open | ITS | TBD | ITS Committee | Student recommendation is to look into NetGear as wireless solution |  | Functionality | 4
4 | ASO | 2011-10-27 | Functionality | Simplify voting on campus software |  | Open | ITS | TBD | IT Analysis |  |  | Functionality | 4
5 | ASO | 2011-10-27 | Support | Email issues: not receiving, problems with updates, and linking |  | Open | ITS | TBD | ITS Analysis |  |  | Functionality | 4
6 | ASO | 2011-10-27 | Support | Concern with myAVC security |  | Open | ITS | TBD | ITS Analysis |  |  | Functionality | 4
7 | ASO | [10 empty] | Functionality | 4
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## Math Science & Engineering
Last Updated by: Calvin Madlock Revised Date: 12/19/2011 | [11 empty] | Business Work Flow | 1 | Open
Math Science & Engineering - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Root Cause/Notes | Cost | Data Conversion | 3
1 | MSE | 2011-11-04 | [9 empty] | Functionality | 4
2 | MSE | 2011-11-04 | [9 empty] | Functionality | 4
3 | MSE | 2011-11-04 | [9 empty] | Functionality | 4
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## Library
Last Updated by: Calvin Madlock Revised Date: 12/19/2011 | [11 empty] | Business Work Flow | 1 | Open
Library - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Root Cause/Notes | Cost | Data Conversion | 3
1 | Library | 2011-11-04 | [9 empty] | Functionality | 4
2 | Library | 2011-11-04 | [9 empty] | Functionality | 4
3 | Library | 2011-11-04 | [9 empty] | Functionality | 4
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## IMC
Last Updated by: Calvin Madlock Revised Date: 12/19/2011 | [11 empty] | Business Work Flow | 1 | Open
IMC - Recommendation Log | [11 empty] | Support
# | Requestor | Date Entered | Issue Type | Issue/Requirement | Priority (SLA) | Status | Assigned To | Date Needed | Next Steps | Resolution/Root Cause/Notes | Cost | Data Conversion | 3
1 | IMC | 2011-11-04 | [9 empty] | Functionality | 4
2 | IMC | 2011-11-04 | [9 empty] | Functionality | 4
3 | IMC | 2011-11-04 | [9 empty] | Functionality | 4
Note on F4: madloccb: 1 = High 2 = Medium 3 = Low

## Banner Users
Notes: ITS Manager Keeps detailed notes on banner users…. See meeting notes from Katherine Mergliano